## Employee Timesheets - Sundew
Employee Name | Comments | Business Unit | Department | Sub Department | Location | Job Title | Reporting To | Client Name | Client Code | Client Manager | Project Name | Project Code | Project Manager | Project State | Phase | Task | Date | Status | Billing Type | Start Time | End Time | Total Hours | Comments | Time Off Type
Manas Maity | 1. Meeting with Team for stand up and review call [DSM] [DONE] |  | Engineering & Products |  | West Bengal | B2 - Sr. Technical Architect | Sarbajit Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | 1. Meeting with Team for stand up and review call [DSM] [DONE]
Manas Maity | 2. Update Learn More CTA Link & Update "Reduced Quote from Liberty Home Guard" content [WCUP-1192] [LIVE] 3. Change Meta Title & Meta Description for State Lobby Page- review changes, go live and testing [WCUP-1189] [LIVE] 4. Make Top Cities on State Pages Optional- review changes, go live and testing [WCUP-1188] [LIVE] 5. OfferIt Voids Returns Audit Tracking [LG-215] [WIP] 6. Tune (Affiliate Platform) Postback Tracking Setup [WCUP-1175] [WIP] 7. Meeting with LHG Dev Team & support [NJ] [DONE] 8. LHG staging/uat/prod migrations [NJ] [DONE] |  | Engineering & Products |  | West Bengal | B2 - Sr. Technical Architect | Sarbajit Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 2. Update Learn More CTA Link & Update "Reduced Quote from Liberty Home Guard" content [WCUP-1192] [LIVE] 3. Change Meta Title & Meta Description for State Lobby Page- review changes, go live and testing [WCUP-1189] [LIVE] 4. Make Top Cities on State Pages Optional- review changes, go live and testing [WCUP-1188] [LIVE] 5. OfferIt Voids Returns Audit Tracking [LG-215] [WIP] 6. Tune (Affiliate Platform) Postback Tracking Setup [WCUP-1175] [WIP] 7. Meeting with LHG Dev Team & support [NJ] [DONE] 8. LHG staging/uat/prod migrations [NJ] [DONE]
Manas Maity | 9. Observation and verification of void returns for all Tiers [NJ] [DONE] |  | Engineering & Products |  | West Bengal | B2 - Sr. Technical Architect | Sarbajit Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Liberty Gate | PC00004 | Pramod Kumar Pradhan, Manas Maity | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 0.5 | 9. Observation and verification of void returns for all Tiers [NJ] [DONE]
Debmalya Ghoshal | DSM and QA task assigned |  | Engineering & Products |  | West Bengal | B2 - Manager | Arnab Mukherjee | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 0.25 | DSM and QA task assigned
Debmalya Ghoshal | DSM & QA assignments |  | Engineering & Products |  | West Bengal | B2 - Manager | Arnab Mukherjee | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Le Roi | PC00008 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 0.25 | DSM & QA assignments
Debmalya Ghoshal | 1. LeROI- Internal DSM & Daily Checklist, Discussed Automation with Adarsh, Checked the manual testing script prepared for Automation with Adarsh 2. Mobile App- Internal DSM, QA Team Allocation, Checked the test cases for Automation 3. LHG- Discussion with Raysa for technical Documentations [Internal Meeting] [Done] 4. LHG- Discussed the QA Team work allocation for the day [Internal Meeting][Done] 5. LHG- Attended the DSM [Internal Meeting][Done] 6. LHG- Checked the overall Deliveries [NJ][Done] 7. LHG- Discussed WCUP-1192 and SYC-4368 with Raysa [WIP] |  | Engineering & Products |  | West Bengal | B2 - Manager | Arnab Mukherjee | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. LeROI- Internal DSM & Daily Checklist, Discussed Automation with Adarsh, Checked the manual testing script prepared for Automation with Adarsh 2. Mobile App- Internal DSM, QA Team Allocation, Checked the test cases for Automation 3. LHG- Discussion with Raysa for technical Documentations [Internal Meeting] [Done] 4. LHG- Discussed the QA Team work allocation for the day [Internal Meeting][Done] 5. LHG- Attended the DSM [Internal Meeting][Done] 6. LHG- Checked the overall Deliveries [NJ][Done] 7. LHG- Discussed WCUP-1192 and SYC-4368 with Raysa [WIP]
Amit Kumar Gupta | 1. Amit: Internal Meeting, Discussion & Documentations [LPP-1065] |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Pramod Kumar Pradhan | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 3 | 1. Amit: Internal Meeting, Discussion & Documentations [LPP-1065]
Amit Kumar Gupta | 2. TEPO Payment Center [VP-85] [WIP] 3. Working on QA's Feedback on other jira related to VP-91. |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Pramod Kumar Pradhan | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 5 | 2. TEPO Payment Center [VP-85] [WIP] 3. Working on QA's Feedback on other jira related to VP-91.
Souvik Mondal | 1. Co-Branded Funnels: GreatWorkPerks & FunExpress [WCUP-1191] [WIP] 2. VP-93: When scheduled appointment appeared in front of tech's unavailable slot, then clicking on unavailable slot the ticket page is opened [IAT-2391] [DONE] |  | Digital Experience |  | West Bengal | A2 - Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Design | HTML Development | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. Co-Branded Funnels: GreatWorkPerks & FunExpress [WCUP-1191] [WIP] 2. VP-93: When scheduled appointment appeared in front of tech's unavailable slot, then clicking on unavailable slot the ticket page is opened [IAT-2391] [DONE]
Souvik Mondal | 3. Souvik: Internal Meeting, Discussion & Documentations [LPP-1058] [WIP] |  | Digital Experience |  | West Bengal | A2 - Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Liberty Gate | PC00004 | Pramod Kumar Pradhan, Manas Maity | Active | Design | Internal Meetings | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | 3. Souvik: Internal Meeting, Discussion & Documentations [LPP-1058] [WIP]
Shahrukh Khan | 1. DSM and review call. [Internal Meeting] [DONE] |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Pramod Kumar Pradhan | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | 1. DSM and review call. [Internal Meeting] [DONE]
Shahrukh Khan | 2. Convert auto-clockout system to use websocket implementation - Worked on the CRON Logic to send realtime updates, Send Notification via Channels. [SYC-105] [WIP] |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Pramod Kumar Pradhan | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 2. Convert auto-clockout system to use websocket implementation - Worked on the CRON Logic to send realtime updates, Send Notification via Channels. [SYC-105] [WIP]
Abinash Padhi | 1. Attended DSM Meeting regarding LHG Project. [NJ] [Done] |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 1 | 1. Attended DSM Meeting regarding LHG Project. [NJ] [Done]
Abinash Padhi | 2. Debug the emulator issue with Firebase.[NJ] [WIP] |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Flutter UI Integration | 2024-11-07 | Not Submitted | Billable |  |  | 4 | 2. Debug the emulator issue with Firebase.[NJ] [WIP]
Abinash Padhi | 3. Addressed to improve internal observations for navigation issue. [LMIN-17] {WIP] |  | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Flutter UI Integration | 2024-11-07 | Not Submitted | Billable |  |  | 3 | 3. Addressed to improve internal observations for navigation issue. [LMIN-17] {WIP]
Dipak Bari | 1. Attended DSM meeting regarding LHG Project. [NJ] [Done] |  | Engineering & Products |  | West Bengal | A2 - Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 1 | 1. Attended DSM meeting regarding LHG Project. [NJ] [Done]
Dipak Bari | 2. Coordinated with peer to start testing on appliance and optional adons part. [LMIN] [Done] |  | Engineering & Products |  | West Bengal | A2 - Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Flutter UI Integration | 2024-11-07 | Not Submitted | Billable |  |  | 2 | 2. Coordinated with peer to start testing on appliance and optional adons part. [LMIN] [Done]
Dipak Bari | 3. Working on nested data structure of child forms. [LMIN-39] [WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Flutter UI Integration | 2024-11-07 | Not Submitted | Billable |  |  | 5 | 3. Working on nested data structure of child forms. [LMIN-39] [WIP]
Aush Paul | 1. Leroi - Process calls stand up & review. [DSM] [DONE] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Le Roi | PC00008 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 0.5 | 1. Leroi - Process calls stand up & review. [DSM] [DONE]
Aush Paul | 2. Refactoring model and query to optimize the de-duping functionality - show custom field data.[LER-390][DONE] 3. Refactoring model and query to optimize the de-duping functionality - show call logs data.[LER-390][DONE] 4. Refactoring model and query to optimize the de-duping functionality - staging functionality testing of bulk recodes for duplicate data .[LER-390][WIP] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Le Roi | PC00008 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Development [Laravel] | 2024-11-07 | Not Submitted | Billable |  |  | 3.5 | 2. Refactoring model and query to optimize the de-duping functionality - show custom field data.[LER-390][DONE] 3. Refactoring model and query to optimize the de-duping functionality - show call logs data.[LER-390][DONE] 4. Refactoring model and query to optimize the de-duping functionality - staging functionality testing of bulk recodes for duplicate data .[LER-390][WIP]
Sandeep Kumar Giri | 1. Attend DSM regarding LHG project. [DSM] [Done] |  | Engineering & Products |  | West Bengal | A2 - Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 1 | 1. Attend DSM regarding LHG project. [DSM] [Done]
Sandeep Kumar Giri | 2. File a claim refactoring testing and resolving issues. [LMIN-39] [WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Flutter UI Integration | 2024-11-07 | Not Submitted | Billable |  |  | 6 | 2. File a claim refactoring testing and resolving issues. [LMIN-39] [WIP]
Sandeep Kumar Giri | 3. Coordination regarding PCF price issue in LIVE. [NJ] [Done] |  | Engineering & Products |  | West Bengal | A2 - Associate | Arup Mondal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Flutter UI Integration | 2024-11-07 | Not Submitted | Billable |  |  | 1 | 3. Coordination regarding PCF price issue in LIVE. [NJ] [Done]
Sujan Kundu | 1. DSM & Standup Call [LPP-1077] [DONE] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Quality Assurance | Internal Updates | 2024-11-07 | Not Submitted | Billable |  |  | 0.75 | 1. DSM & Standup Call [LPP-1077] [DONE]
Sujan Kundu | 1. Checked the daily LIVE checklist [LPP-1078] [DONE] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Quality Assurance | Regression Testing | 2024-11-07 | Not Submitted | Billable |  |  | 0.75 | 1. Checked the daily LIVE checklist [LPP-1078] [DONE]
Sujan Kundu | 1. Payment is not applied to the correct policy [SYC-4369][DONE] 2. SYCO is charging customers incorrectly if the amount is in the thousands [SYC-4367][DONE] 3. New Merchant Processor Setup (Micamp) [SYC-3449][Checked feedback] 4. Calendar and Scheduling [VP-93][WIP] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Quality Assurance | Functional Testing | 2024-11-07 | Not Submitted | Billable |  |  | 6.5 | 1. Payment is not applied to the correct policy [SYC-4369][DONE] 2. SYCO is charging customers incorrectly if the amount is in the thousands [SYC-4367][DONE] 3. New Merchant Processor Setup (Micamp) [SYC-3449][Checked feedback] 4. Calendar and Scheduling [VP-93][WIP]
Pritam Bhattacharyya | Attend DSM and Review Call [DSM] [DONE] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Attend DSM and Review Call [DSM] [DONE]
Pritam Bhattacharyya | 1. Pop-up in Editing Cancellation Requests and Commission Entry in Manage Cancelled Policies Module. [SYC-4368 P3/B][Done] 2. Customer Review & Rating Module Rework [SYC-3903 P2/E] [WIP] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 6 | 1. Pop-up in Editing Cancellation Requests and Commission Entry in Manage Cancelled Policies Module. [SYC-4368 P3/B][Done] 2. Customer Review & Rating Module Rework [SYC-3903 P2/E] [WIP]
Pritam Bhattacharyya | Team discussion and support for other tasks |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | KT and Project Understanding | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Team discussion and support for other tasks
Prasenjit Karmakar | 1) Discuss with the application team with the logic and analysis for manager wise task status progression change and progression status change in coatomer level report.(CDS - 128) 2)Create metrics in SQL and power bi for call answered in 20s, 25s 30s etc. Ctrate DDL and discuss about the new aggregated table for AWS connect data.(WPM - 11) |  | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Report Development | 2024-11-07 | Waiting for Approval | Billable |  |  | 8 | 1) Discuss with the application team with the logic and analysis for manager wise task status progression change and progression status change in coatomer level report.(CDS - 128) 2)Create metrics in SQL and power bi for call answered in 20s, 25s 30s etc. Ctrate DDL and discuss about the new aggregated table for AWS connect data.(WPM - 11)
Ananya Chatterjee | 1. Adding Badges/Tags for FOP (Fraternal Order of Police) and LE Energy Policies on SYCO [SYC-4199] [STAGING] 2. Review Meeting [Internal Meeting] [DONE] 3. Update the Learn More CTA Link & Update the "Reduced Quote from Liberty Home Guard" content [WCUP-1192] [DONE] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Quality Assurance | Functional Testing | 2024-11-07 | Waiting for Approval | Billable |  |  | 8 | 1. Adding Badges/Tags for FOP (Fraternal Order of Police) and LE Energy Policies on SYCO [SYC-4199] [STAGING] 2. Review Meeting [Internal Meeting] [DONE] 3. Update the Learn More CTA Link & Update the "Reduced Quote from Liberty Home Guard" content [WCUP-1192] [DONE]
Mamata Ojha | 1. Mamata - Internal Team Meeting, Discussion & Documentation [LPP-1071] [WIP] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Quality Assurance | Internal Updates | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | 1. Mamata - Internal Team Meeting, Discussion & Documentation [LPP-1071] [WIP]
Mamata Ojha | 2. Checked over LIVE & replied back over JIRA [SYC-3954] [Done] 3. Checked over STAGING & replied back over JIRA [SYC-3939] [Done] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Quality Assurance | Functional Testing | 2024-11-07 | Waiting for Approval | Billable |  |  | 2.5 | 2. Checked over LIVE & replied back over JIRA [SYC-3954] [Done] 3. Checked over STAGING & replied back over JIRA [SYC-3939] [Done]
Mamata Ojha | 3. Checked over LIVE & updated on release sheet [WCUP-1189, WCUP-1188,SYC-4368] [Done] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Quality Assurance | Regression Testing | 2024-11-07 | Waiting for Approval | Billable |  |  | 4 | 3. Checked over LIVE & updated on release sheet [WCUP-1189, WCUP-1188,SYC-4368] [Done]
Mamata Ojha | 5. Checked the Daily LIVE Checklist for Website, Website Backend [Done] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Debmalya Ghoshal | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Quality Assurance | Regression Testing | 2024-11-07 | Waiting for Approval | Billable |  |  | 0.5 | 5. Checked the Daily LIVE Checklist for Website, Website Backend [Done]
Tanushree Roy | 1. DSM & review meeting [LPP-1076] [Done] 2. Resolved the internal issue related to pro-series item PCF. [LPP-1076] [LIVE] 2. Internal discussion regarding the diagnostic form save. [LPP-1076] [Done] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 3 | 1. DSM & review meeting [LPP-1076] [Done] 2. Resolved the internal issue related to pro-series item PCF. [LPP-1076] [LIVE] 2. Internal discussion regarding the diagnostic form save. [LPP-1076] [Done]
Tanushree Roy | 1. Created an API to save the gutter diagnostic form. [VP-132] [Completed Locally] 2. Started working on the final submission of the diagnostic form API. [VP-133] [WIP] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Mobile App | PC00007 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | API Development | 2024-11-07 | Waiting for Approval | Billable |  |  | 5 | 1. Created an API to save the gutter diagnostic form. [VP-132] [Completed Locally] 2. Started working on the final submission of the diagnostic form API. [VP-133] [WIP]
Jayanta Paul | 1) GDE-46: Did RCA and provided detailed explanation about missing transactions. 2) Created users in AWS console and given access to S3, Athena and Connect services. 3) Communicated with Sar regarding the access for workforce and Ansible data. |  | Analytics & Automation |  | West Bengal | A3 - Sr. Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Development [Generic] | 2024-11-07 | Not Submitted | Billable |  |  | 3.5 | 1) GDE-46: Did RCA and provided detailed explanation about missing transactions. 2) Created users in AWS console and given access to S3, Athena and Connect services. 3) Communicated with Sar regarding the access for workforce and Ansible data.
Jayanta Paul | 1) Call with LHG Ops and Workforce team. 2) Meeting with Marking team |  | Analytics & Automation |  | West Bengal | A3 - Sr. Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Client Reviews | 2024-11-07 | Not Submitted | Billable |  |  | 1.5 | 1) Call with LHG Ops and Workforce team. 2) Meeting with Marking team
Jayanta Paul | 1) Internal DSM. 2) Discussion with team about date calculation logic for sales fact. 3) GDE-45: Went thought the requirement and discussion with team about the extraction of data from database. |  | Analytics & Automation |  | West Bengal | A3 - Sr. Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 1.5 | 1) Internal DSM. 2) Discussion with team about date calculation logic for sales fact. 3) GDE-45: Went thought the requirement and discussion with team about the extraction of data from database.
Jayanta Paul | State value mapping with offerit and Everflow data for Lead Report |  | Analytics & Automation |  | West Bengal | A3 - Sr. Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Report Development | 2024-11-07 | Not Submitted | Billable |  |  | 1 | State value mapping with offerit and Everflow data for Lead Report
Rajdeep Taluckdar | Daily DSM |  | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 0.75 | Daily DSM
Rajdeep Taluckdar | WPM-15: Developed and tested the call connect aggregate table and loaded the data for two months |  | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Development [Generic] | 2024-11-07 | Not Submitted | Billable |  |  | 6 | WPM-15: Developed and tested the call connect aggregate table and loaded the data for two months
Rajdeep Taluckdar | WPM-15 : Team meeting regarding structure of call connect aggregate table |  | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 1.25 | WPM-15 : Team meeting regarding structure of call connect aggregate table
Riju Ghosh | 1. Leroi - Process calls stand up & review. [DSM] [DONE] |  | Engineering & Products |  | West Bengal | A2 - Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Le Roi | PC00008 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Internal Meeting | 2024-11-07 | Not Submitted | Billable |  |  | 0.25 | 1. Leroi - Process calls stand up & review. [DSM] [DONE]
Riju Ghosh | 2. Reduce multiple API calls to the same API endpoint - process the queue using background job. [LER-404] [DONE] 3. Optimization of Contact De-Duping - supervised the date filter implementation. [LER-377] [DONE] 4. Optimization of Contact De-Duping - supervised the implementation of query conditions. [LER-377] [DONE] 5. Reduce multiple API calls to the same API endpoint - change the data structure of the intellective routing priorities. [LER-404] [WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Le Roi | PC00008 | Pramod Kumar Pradhan, Arup Mondal | Active | Development | Development [Laravel] | 2024-11-07 | Not Submitted | Billable |  |  | 7 | 2. Reduce multiple API calls to the same API endpoint - process the queue using background job. [LER-404] [DONE] 3. Optimization of Contact De-Duping - supervised the date filter implementation. [LER-377] [DONE] 4. Optimization of Contact De-Duping - supervised the implementation of query conditions. [LER-377] [DONE] 5. Reduce multiple API calls to the same API endpoint - change the data structure of the intellective routing priorities. [LER-404] [WIP]
Ratul Rakshit | 1. Add "Paid in full" as option for 'Adjust the payment plan' in 'Downgrade the customer' [SYC-4295] [Staging] 2. Updating how we track renewals and their associated utilization of policy numbers [SYC-835] [WIP] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 4 | 1. Add "Paid in full" as option for 'Adjust the payment plan' in 'Downgrade the customer' [SYC-4295] [Staging] 2. Updating how we track renewals and their associated utilization of policy numbers [SYC-835] [WIP]
Ratul Rakshit | 1. Attended DSM and review call [DONE] 2. Internal meeting with Sharukh regarding SYC-3939 [Done] 3. Internal meeting with Samim regarding RA payment. [Done] |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 2 | 1. Attended DSM and review call [DONE] 2. Internal meeting with Sharukh regarding SYC-3939 [Done] 3. Internal meeting with Samim regarding RA payment. [Done]
Ratul Rakshit | 1. KT to Ashok about the Retention form. |  | Engineering & Products |  | West Bengal | A1 - Executive Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | KT and Project Understanding | 2024-11-07 | Waiting for Approval | Billable |  |  | 2 | 1. KT to Ashok about the Retention form.
Sayon Jana | 1. Sayon: Internal Meeting, Discussion & Documentations [LPP-1066][WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | 1. Sayon: Internal Meeting, Discussion & Documentations [LPP-1066][WIP]
Sayon Jana | 1. SYCO ¦ Maintenance diagnostic form implementation [SYC-4046][WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. SYCO ¦ Maintenance diagnostic form implementation [SYC-4046][WIP]
Lokanath Dey | Weekly LHG meeting | Sun Dew Solutions Private Limited | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Requirement Gathering | Client Meeting | 2024-11-07 | Not Submitted | Non Billable |  |  | 1 | Weekly LHG meeting
Lokanath Dey | On CDS-136: 1. Analyze Bugs raised by the client, gather the requirements, analyze related tables and columns, retrieve the OPERATIONAL_CANCELLED_POLICIES_MANIFEST.pbix report from the drive, connect the production database environment to the PBIX report, and refresh with the latest values. On MDSC- 737: 1. Connect the Production environment database to ANALYTICAL_POLICY_BY_TIME dashboard using the Power Query Editor. 2. Testing the all matrix with production database. 3. Created the test document with matching data. | Sun Dew Solutions Private Limited | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Report Development | 2024-11-07 | Not Submitted | Non Billable |  |  | 7 | On CDS-136: 1. Analyze Bugs raised by the client, gather the requirements, analyze related tables and columns, retrieve the OPERATIONAL_CANCELLED_POLICIES_MANIFEST.pbix report from the drive, connect the production database environment to the PBIX report, and refresh with the latest values. On MDSC- 737: 1. Connect the Production environment database to ANALYTICAL_POLICY_BY_TIME dashboard using the Power Query Editor. 2. Testing the all matrix with production database. 3. Created the test document with matching data.
Somnath Haldar | Somnath: Internal Meeting, Discussion & Documentations [LPP-1059] [WIP] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Design | Internal Meetings | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Somnath: Internal Meeting, Discussion & Documentations [LPP-1059] [WIP]
Somnath Haldar | 1. BIC Design enhancements [WCUP-1179] [WIP] 2. Design Works for Hunting Module [SYC-4266] [Done] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A3 - Sr. Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Design | HTML Development | 2024-11-07 | Waiting for Approval | Billable |  |  | 6 | 1. BIC Design enhancements [WCUP-1179] [WIP] 2. Design Works for Hunting Module [SYC-4266] [Done]
Raysa Dey | 1. Updated Cancellation Request tech doc as per client feedback [LPP-691] [Done] 2. Shared Cancellation Request tech document for internal review LPP-691] [Done] 3. Initial discussion regarding the Claim Payout Requests module [LPP-1046 & LPP-1047] [WIP] 4. Working on Customer Payout Requests tech doc [LPP-1046] [WIP] 5. Working on Service Provider (Technician) Payout Requests tech doc [LPP-1047] [WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Requirement Gathering | Requirement Document | 2024-11-07 | Waiting for Approval | Billable |  |  | 6.75 | 1. Updated Cancellation Request tech doc as per client feedback [LPP-691] [Done] 2. Shared Cancellation Request tech document for internal review LPP-691] [Done] 3. Initial discussion regarding the Claim Payout Requests module [LPP-1046 & LPP-1047] [WIP] 4. Working on Customer Payout Requests tech doc [LPP-1046] [WIP] 5. Working on Service Provider (Technician) Payout Requests tech doc [LPP-1047] [WIP]
Sumit Kumar Jogi | DSM: GDE-30 to be carried out | Sun Dew Solutions Private Limited | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | DSM: GDE-30 to be carried out
Sumit Kumar Jogi | GDE-30: 1. Hadoop installation and system path env variables setup for proper generation of parquet files, sample files dump to S3 bucket using Talend job and testing -- done. 2. Creating campaign & email tables in AWS for testing of ETL job -- in progress. | Sun Dew Solutions Private Limited | Analytics & Automation |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Design | ETL Design | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | GDE-30: 1. Hadoop installation and system path env variables setup for proper generation of parquet files, sample files dump to S3 bucket using Talend job and testing -- done. 2. Creating campaign & email tables in AWS for testing of ETL job -- in progress.
Soumyajit Ball | 1. Prospective Technician Module[SYC-4263][SYC-4262][WIP] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. Prospective Technician Module[SYC-4263][SYC-4262][WIP]
Soumyajit Ball | Attended DSM and review call | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Attended DSM and review call
Samim Molla | 1. Worked on sending the payment receipt email when a customer charges for RAs via the ticket page. [SYC-1048] [WIP] 2. Worked on sending the payment receipt email when a customer charges for RA via CUPO.[SYC-1048] [WIP] 3. Worked on sending the payment receipt email when a customer charges for RA via email deep link.[SYC-1048] [WIP] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. Worked on sending the payment receipt email when a customer charges for RAs via the ticket page. [SYC-1048] [WIP] 2. Worked on sending the payment receipt email when a customer charges for RA via CUPO.[SYC-1048] [WIP] 3. Worked on sending the payment receipt email when a customer charges for RA via email deep link.[SYC-1048] [WIP]
Samim Molla | Attended DSM and review call | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Attended DSM and review call
Asutosh Roy | Internal meeting attended |  | Engineering & Products |  | West Bengal | A2 - Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Internal meeting attended
Asutosh Roy | Adjusting the Proforma PDF [SYC-3523] [CUPO PART] [Internal QA / STAGING] has developed with the following points - 1. Code flow and dependencies checked over CUPO for downloding invoice 2. Modification of Proforma Invoice done 3. proforma is PENDING or PAID status checking logic added in the controlle 5. Invoice pdf modified according to payment status 6. Price amount modified if sales tax is applied upon full amount 7. Sales tax tested with different scenarios 8. Sales tax removed for certain scenarios 9. Made (Price - Sales Tax) as total price 10. PAID , SALES TAX columns are added in the invoice 11. Sub total row has removed now 12. Condition applied to show “Sales Tax” in the case where Sales Tax has included with in total amount 13. If the status of the proforma is PENDING, then when the invoice is downloaded it should NOT displaying the Paid row hide done |  | Engineering & Products |  | West Bengal | A2 - Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 5 | Adjusting the Proforma PDF [SYC-3523] [CUPO PART] [Internal QA / STAGING] has developed with the following points - 1. Code flow and dependencies checked over CUPO for downloding invoice 2. Modification of Proforma Invoice done 3. proforma is PENDING or PAID status checking logic added in the controlle 5. Invoice pdf modified according to payment status 6. Price amount modified if sales tax is applied upon full amount 7. Sales tax tested with different scenarios 8. Sales tax removed for certain scenarios 9. Made (Price - Sales Tax) as total price 10. PAID , SALES TAX columns are added in the invoice 11. Sub total row has removed now 12. Condition applied to show “Sales Tax” in the case where Sales Tax has included with in total amount 13. If the status of the proforma is PENDING, then when the invoice is downloaded it should NOT displaying the Paid row hide done
Asutosh Roy | Adding Badges/Tags for FOP (Fraternal Order of Police) and LE Energy Policies on SYCO (SYC-4199) [Internal QA / STAGING] 1. LE energy badge is broken on claim page ix fixed over STAGING 2. Currently badges are in very poor and blurry quality - had a discussion with team for the implementation 3. Code pushed over STAGING and tested |  | Engineering & Products |  | West Bengal | A2 - Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Adding Badges/Tags for FOP (Fraternal Order of Police) and LE Energy Policies on SYCO (SYC-4199) [Internal QA / STAGING] 1. LE energy badge is broken on claim page ix fixed over STAGING 2. Currently badges are in very poor and blurry quality - had a discussion with team for the implementation 3. Code pushed over STAGING and tested
Asutosh Roy | SYCO Sales ¦ Create a new default floor table and a CRON to reset the active floor to the default (SYC-4259) [WIP] - Has developed with the following points 1. Migrations added for the following modules 2. Add and edit form modified |  | Engineering & Products |  | West Bengal | A2 - Associate | Anup Pramanik | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | SYCO Sales ¦ Create a new default floor table and a CRON to reset the active floor to the default (SYC-4259) [WIP] - Has developed with the following points 1. Migrations added for the following modules 2. Add and edit form modified
Sayantani Chatterjee | Internal DSM |  | Analytics & Automation |  | West Bengal | A1 - Executive Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Non Billable |  |  | 0.5 | Internal DSM
Sayantani Chatterjee | MDSC-738: working on the cancellation fields from the ods_orders_tracking table within the sales_fact job. |  | Analytics & Automation |  | West Bengal | A1 - Executive Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Development [Generic] | 2024-11-07 | Waiting for Approval | Non Billable |  |  | 7.5 | MDSC-738: working on the cancellation fields from the ods_orders_tracking table within the sales_fact job.
Swarup Das | 1. Linking technicians invoices to Manage Service Provider Payout Requests [SYC-4336] [QA] 2. Update Payment Method Display for SIBI Supplier to "Net 30-90" [SYC-4286] [QA] 3. Implementing changes in the Manage Customer Payout Request Module. [SYC-4244] [WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. Linking technicians invoices to Manage Service Provider Payout Requests [SYC-4336] [QA] 2. Update Payment Method Display for SIBI Supplier to "Net 30-90" [SYC-4286] [QA] 3. Implementing changes in the Manage Customer Payout Request Module. [SYC-4244] [WIP]
Swarup Das | Swarup-Internal Team Meeting, Discussion & Documentation [LPP-1067] [WIP] |  | Engineering & Products |  | West Bengal | A2 - Associate | Amit Kumar Gupta | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Swarup-Internal Team Meeting, Discussion & Documentation [LPP-1067] [WIP]
Aratrika Sarkar | LPP- 1047 Technician Payout Request [Done] LPP-691 Cancellation Request [Edited- Done] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-SYCO | PC00001 | Pramod Kumar Pradhan, Anup Pramanik, Amit Kumar Gupta | Active | Requirement Gathering | Requirement Document | 2024-11-07 | Not Submitted | Billable |  |  | 8 | LPP- 1047 Technician Payout Request [Done] LPP-691 Cancellation Request [Edited- Done]
Suvam Roy | Internal DSM | Sun Dew Solutions Private Limited | Analytics & Automation |  | West Bengal | A1 - Executive Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Non Billable |  |  | 1 | Internal DSM
Suvam Roy | GDE - 45 Understanding of the requirements and internal email reports. Development for BG1 affiliate for total leads and rolling two days percentile. | Sun Dew Solutions Private Limited | Analytics & Automation |  | West Bengal | A1 - Executive Associate | Anwesha Das | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Data Analytics | PC00010 | Anwesha Das, Jayanta Paul | Active | Development | Development [Python] | 2024-11-07 | Waiting for Approval | Non Billable |  |  | 7 | GDE - 45 Understanding of the requirements and internal email reports. Development for BG1 affiliate for total leads and rolling two days percentile.
Sourav Bhowmik | 1. Worked On Review rating implementation as per requirement (WCUP-1177) [Local] | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Development | Development [Laravel] | 2024-11-07 | Waiting for Approval | Billable |  |  | 7 | 1. Worked On Review rating implementation as per requirement (WCUP-1177) [Local]
Sourav Bhowmik | Attended DSM and review call. | Sun Dew Solutions Private Limited | Engineering & Products |  | West Bengal | A2 - Associate | Manas Maity | Liberty Home Guard | AC001 | Sarbajit Das | LHG-Website and CUPO | PC00002 | Pramod Kumar Pradhan, Manas Maity, Anup Pramanik | Active | Development | Internal Meeting | 2024-11-07 | Waiting for Approval | Billable |  |  | 1 | Attended DSM and review call.
This report is generated by Keka HR and Payroll Software